## Sheet1
MAJOR RISKS
Risk ID | Risk Title | Description | Impact | Likelihood | Mitigation | Owner
R-001 | Venue Cancellation | Venue might become unavailable due to unforeseen issues. | High | Medium | Have a backup venue; include cancellation clause in contract. | Logistics Lead
R-002 | Cybersecurity Breach | Event registration system might get hacked, exposing attendee data. | High | Low | Use multi-factor authentication; partner with cybersecurity firm. | IT Security
R-003 | Keynote Speaker No-Show | A major speaker might cancel, affecting event reputation. | High | Medium | Arrange backup speakers; include contingency clauses in speaker contracts. | HR
MINOR RISKS
Risk ID | Risk Title | Description | Impact | Likelihood | Mitigation | Owner
R-004 | Internet Downtime | Wi-Fi outage may disrupt digital presentations or interactions. | Medium | Medium | Contract with multiple ISPs; have offline backups of key materials. | IT Team
R-005 | Volunteer No-Shows | Staff or volunteers might fail to show up. | Low | High | Maintain a reserve list; offer incentives. | HR Coordinator
R-006 | Language Barriers | Some attendees may not understand English-only sessions. | Medium | Low | Offer translation services; provide multilingual signage. | Communications Lead
1) Risk Monitoring & Reporting Section:
Risk Review Frequency: Weekly risk review meetings during the 4-week planning phase.
Reporting: Status updates shared in project WhatsApp group & Google Sheet.
Escalation: High risks escalated immediately to project sponsor.
2) Assumptions Section:
All vendors and stakeholders have confirmed availability.
Internet services remain stable for all team members.
Backup options (speakers/venues) will be available with 48-hour notice.
Team members will be available for daily updates.